## Dashboard
Scrum Team Management Dashboard |  |  |  |  | 1-Oct-19 to 31-Oct-19
Story # | Assignee | Task Name | Start Date | Duration (Hr) | End Date | Status | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25
SP2-00001 | Backend Developer 1 | Release preparation | 2019-10-02 | 5 | 2019-10-02 | Completed
| Backend Developer 2 | Release preparation | 2019-10-02 | 5 | 2019-10-02 | Completed
| Backend Developer 3 | Release deployment | 2019-10-02 | 4 | 2019-10-02 | Completed
| Frontend Developer 1 | Release preparation | 2019-10-01 | 5 | 2019-10-01 | Completed
| Frontend Developer 2 | Release preparation | 2019-10-01 | 5 | 2019-10-01 | Completed
SP2-00002 | Backend Developer 1 | Release deployment | 2019-10-03 | 2 | 2019-10-03 | Completed
| Frontend Developer 1 | Release deployment | 2019-10-02 | 6 | 2019-10-02 | Completed
| Frontend Developer 2 | Code Quality Check (Frontend) | 2019-10-02 | 6 | 2019-10-02 | Completed
SP2-00003 | Backend Developer 3 | Incident Investigation | 2019-10-02 | 6 | 2019-10-03 | Completed
| Frontend Developer 1 | Incident Investigation | 2019-10-03 | 8 | 2019-10-04 | Completed
| Frontend Developer 2 | Incident Investigation | 2019-10-03 | 8 | 2019-10-04 | Completed
SP2-00004 | Backend Developer 3 | Incident Investigation | 2019-10-03 | 6 | 2019-10-04 | Completed
| Backend Developer 4 | Incident Investigation | 2019-10-02 | 8 | 2019-10-03 | Completed
| Backend Developer 5 | Incident Investigation | 2019-10-02 | 8 | 2019-10-03 | Completed
| Frontend Developer 2 | Incident Investigation | 2019-10-04 | 8 | 2019-10-07 | Completed
|  |  | 2019-10-08 | 8 | 2019-10-09 | Completed
| Frontend Developer 3 | Incident Investigation | 2019-10-01 | 8 | 2019-10-02 | Completed
SP2-00005 | Backend Developer 3 | Test case creation | 2019-10-04 | 6 | 2019-10-07 | Completed
| Backend Developer 4 | Technical discussion (Backend) | 2019-10-03 | 3 | 2019-10-03 | Completed
| Backend Developer 5 | Frontend dev | 2019-10-03 | 8 | 2019-10-04 | Completed
| Frontend Developer 1 | Peer code review (Frontend) | 2019-10-07 | 8 | 2019-10-08 | Completed
| Frontend Developer 2 | SIT | 2019-10-09 | 8 | 2019-10-10 | Completed
| Frontend Developer 3 | Code Quality Check (Frontend) | 2019-10-02 | 8 | 2019-10-03 | Completed
SP2-00006 | Frontend Developer 2 | Peer code review (Frontend) | 2019-10-10 | 2 | 2019-10-10 | Completed
| Frontend Developer 3 | Code Quality Check (Frontend) | 2019-10-15 | 2 | 2019-10-15 | Completed
|  | Demo | 2019-10-21 | 2 | 2019-10-21 | Not Started
|  |  | 2019-10-03 | 2 | 2019-10-03 | Completed
|  | Frontend dev | 2019-10-09 | 24 | 2019-10-15 | Completed
|  | SIT | 2019-10-16 | 18 | 2019-10-18 | Completed
|  | WA dev | 2019-10-22 | 24 | 2019-10-31 | Not Started
|  |  | 2019-10-03 | 24 | 2019-10-09 | Completed
SP2-00007 | Frontend Developer 2 | Code Quality Check (Frontend) | 2019-10-22 | 4 | 2019-10-22 | Not Started
|  | Demo | 2019-10-25 | 2 | 2019-10-25 | Not Started
|  | Frontend dev | 2019-10-15 | 30 | 2019-10-21 | In Progress
|  | SIT | 2019-10-23 | 8 | 2019-10-24 | Not Started
|  | Technical discussion (Frontend) | 2019-10-11 | 4 | 2019-10-11 | Completed
|  | Test case creation | 2019-10-14 | 4 | 2019-10-14 | Completed
|  | WA dev | 2019-10-28 | 24 | 2019-10-31 | Not Started
| Frontend Developer 5 | Peer code review (Frontend) | 2019-10-01 | 4 | 2019-10-01 | Completed
SP2-00008 | Backend Developer 2 | Peer code review (backend) | 2019-10-02 | 2 | 2019-10-03 | Completed
| Backend Developer 5 | Backend dev | 2019-10-08 | 6 | 2019-10-08 | Completed
|  | Code Quality Check (backend) | 2019-10-09 | 2 | 2019-10-09 | Completed
|  | SIT | 2019-10-10 | 3 | 2019-10-10 | Completed
|  | Technical discussion (Backend) | 2019-10-07 | 3 | 2019-10-07 | Completed
|  | Test case creation | 2019-10-07 | 3 | 2019-10-07 | Completed
|  | Unit Test | 2019-10-09 | 4 | 2019-10-09 | Completed
SP2-00009 | Backend Developer 1 | Peer code review (backend) | 2019-10-03 | 2 | 2019-10-03 | Completed
| Backend Developer 5 | Backend dev | 2019-10-11 | 8 | 2019-10-14 | Completed
|  | Code Quality Check (backend) | 2019-10-14 | 1 | 2019-10-14 | Completed
|  | SIT | 2019-10-15 | 3 | 2019-10-15 | Completed
|  | Technical discussion (Backend) | 2019-10-10 | 3 | 2019-10-10 | Completed
|  | Test case creation | 2019-10-11 | 2 | 2019-10-11 | Completed
|  | Unit Test | 2019-10-15 | 3 | 2019-10-15 | Completed
SP2-00010 | Backend Developer 2 | Peer code review (backend) | 2019-10-03 | 2 | 2019-10-03 | Completed
| Backend Developer 3 | Backend dev | 2019-10-08 | 6 | 2019-10-08 | Completed
|  | Code Quality Check (backend) | 2019-10-09 | 1 | 2019-10-09 | Completed
|  | Demo | 2019-10-11 | 1 | 2019-10-11 | Completed
|  | SIT | 2019-10-10 | 7 | 2019-10-11 | Completed
|  | Technical discussion (Backend) | 2019-10-07 | 2 | 2019-10-07 | Completed
|  | Test case creation | 2019-10-07 | 2 | 2019-10-07 | Completed
|  | Unit Test | 2019-10-09 | 4 | 2019-10-09 | Completed
| Frontend Developer 5 | CMS dev | 2019-10-02 | 8 | 2019-10-03 | Completed
|  | Code Quality Check (Frontend) | 2019-10-08 | 2 | 2019-10-08 | Completed
|  | Frontend dev | 2019-10-04 | 6 | 2019-10-04 | Completed
|  | Peer code review (Frontend) | 2019-10-07 | 2 | 2019-10-07 | Completed
|  | Technical discussion (Frontend) | 2019-10-01 | 4 | 2019-10-02 | Completed
|  | WA dev | 2019-10-07 | 3 | 2019-10-08 | Completed
SP2-00011 | Backend Developer 1 | Backend dev | 2019-10-04 | 24 | 2019-10-09 | Completed
| Backend Developer 5 | Technical discussion (Backend) | 2019-10-16 | 8 | 2019-10-17 | Completed
| Frontend Developer 1 | Technical discussion (Frontend) | 2019-10-08 | 8 | 2019-10-09 | Completed
| Frontend Developer 4 | Technical discussion (Backend) | 2019-10-02 | 8 | 2019-10-03 | Completed
|  | Technical discussion (Frontend) | 2019-10-01 | 8 | 2019-10-02 | Completed
SP2-00012 | Backend Developer 2 | Backend dev | 2019-10-07 | 24 | 2019-10-10 | Completed
|  | SIT | 2019-10-11 | 6 | 2019-10-11 | Completed
|  | Technical discussion (Backend) | 2019-10-04 | 6 | 2019-10-04 | Completed
|  |  | 2019-10-14 | 2 | 2019-10-14 | Completed
SP2-00013 | Backend Developer 2 | SIT | 2019-10-14 | 2 | 2019-10-14 | Completed
SP2-00014 | Frontend Developer 4 | CMS dev | 2019-10-07 | 2 | 2019-10-07 | Completed
|  | Code Quality Check (Frontend) | 2019-10-15 | 1 | 2019-10-15 | Completed
|  | Demo | 2019-10-15 | 1 | 2019-10-15 | Completed
|  | Frontend dev | 2019-10-08 | 30 | 2019-10-14 | Completed
|  | SIT | 2019-10-15 | 1 | 2019-10-15 | Completed
|  | Technical discussion (Frontend) | 2019-10-04 | 4 | 2019-10-04 | Completed
|  | Test case creation | 2019-10-04 | 2 | 2019-10-04 | Completed
| Frontend Developer 5 | Peer code review (Frontend) | 2019-10-08 | 2 | 2019-10-08 | Completed
SP2-00015 | Backend Developer 3 | Technical discussion (Frontend) | 2019-10-11 | 8 | 2019-10-14 | Completed
| Frontend Developer 5 | Technical discussion (Frontend) | 2019-10-09 | 8 | 2019-10-10 | Completed
SP2-00016 | Backend Developer 1 | Backend dev | 2019-10-10 | 9 | 2019-10-11 | Completed
|  | Code Quality Check (backend) | 2019-10-21 | 2 | 2019-10-21 | Not Started
|  | Test case creation | 2019-10-10 | 1 | 2019-10-10 | Completed
| Backend Developer 2 | Demo | 2019-10-23 | 6 | 2019-10-23 | Not Started
|  | SIT | 2019-10-22 | 6 | 2019-10-22 | Not Started
|  | Technical discussion (Backend) | 2019-10-18 | 4 | 2019-10-21 | Completed
|  | Unit Test | 2019-10-21 | 6 | 2019-10-21 | Not Started
| Backend Developer 4 | Peer code review (backend) | 2019-10-04 | 2 | 2019-10-04 | Completed
SP2-00017 | Backend Developer 1 | Peer code review (backend) | 2019-10-21 | 1 | 2019-10-21 | Not Started
| Backend Developer 4 | Backend dev | 2019-10-07 | 24 | 2019-10-11 | Completed
|  | Code Quality Check (backend) | 2019-10-14 | 1 | 2019-10-14 | Completed
|  | Demo | 2019-10-17 | 1 | 2019-10-17 | Completed
|  | SIT | 2019-10-14 | 18 | 2019-10-17 | Completed
|  | Technical discussion (Backend) | 2019-10-04 | 2 | 2019-10-04 | Completed
|  | Test case creation | 2019-10-07 | 2 | 2019-10-07 | Completed
|  | Unit Test | 2019-10-14 | 4 | 2019-10-14 | Completed
SP2-00018 | Frontend Developer 4 | CMS dev | 2019-10-16 | 24 | 2019-10-21 | In Progress
|  | Code Quality Check (Frontend) | 2019-10-23 | 1 | 2019-10-23 | Not Started
|  | Demo | 2019-10-23 | 1 | 2019-10-23 | Not Started
|  | Frontend dev | 2019-10-22 | 4 | 2019-10-22 | Not Started
|  | SIT | 2019-10-23 | 1 | 2019-10-23 | Not Started
|  | Technical discussion (Frontend) | 2019-10-15 | 2 | 2019-10-15 | Completed
|  | Test case creation | 2019-10-15 | 1 | 2019-10-15 | Completed
| Frontend Developer 5 | Peer code review (Frontend) | 2019-10-10 | 2 | 2019-10-10 | Completed
SP2-00019 | Frontend Developer 4 | Peer code review (Frontend) | 2019-10-23 | 2 | 2019-10-23 | Not Started
| Frontend Developer 5 | CMS dev | 2019-10-11 | 22 | 2019-10-17 | Completed
|  | Code Quality Check (Frontend) | 2019-10-23 | 2 | 2019-10-23 | Not Started
|  | Demo | 2019-10-23 | 1 | 2019-10-23 | Not Started
|  | Frontend dev | 2019-10-17 | 24 | 2019-10-22 | In Progress
|  | SIT | 2019-10-23 | 2 | 2019-10-23 | Not Started
|  | Technical discussion (Frontend) | 2019-10-10 | 2 | 2019-10-10 | Completed
|  | Test case creation | 2019-10-11 | 2 | 2019-10-11 | Completed
|  | WA dev | 2019-10-24 | 4 | 2019-10-24 | Not Started
SP2-00020 | Backend Developer 3 | Peer code review (backend) | 2019-10-14 | 1 | 2019-10-14 | In Progress
| Backend Developer 5 | Backend dev | 2019-10-18 | 4 | 2019-10-18 | Completed
|  | Code Quality Check (backend) | 2019-10-18 | 1 | 2019-10-18 | Completed
|  | SIT | 2019-10-28 | 4 | 2019-10-28 | Not Started
|  | Technical discussion (Backend) | 2019-10-17 | 1 | 2019-10-17 | Completed
|  | Unit Test | 2019-10-28 | 2 | 2019-10-28 | Not Started
| Frontend Developer 1 | CMS dev | 2019-10-11 | 24 | 2019-10-16 | Completed
|  | Code Quality Check (Frontend) | 2019-10-30 | 6 | 2019-10-30 | Not Started
|  | Demo | 2019-10-31 | 1 | 2019-10-31 | Not Started
|  | Frontend dev | 2019-10-17 | 24 | 2019-10-22 | In Progress
|  | Technical discussion (Frontend) | 2019-10-09 | 2 | 2019-10-09 | Completed
|  | Test case creation | 2019-10-10 | 6 | 2019-10-10 | Completed
| Frontend Developer 5 | Peer code review (Frontend) | 2019-10-24 | 2 | 2019-10-24 | Not Started
SP2-00021 | Backend Developer 3 | Backend dev | 2019-10-15 | 24 | 2019-10-18 | In Progress
|  | Code Quality Check (backend) | 2019-10-31 | 1 | 2019-10-31 | Not Started
|  | Demo | 2019-10-31 | 1 | 2019-10-31 | Not Started
|  | SIT | 2019-10-31 | 2 | 2019-10-31 | Not Started
|  | Technical discussion (Backend) | 2019-10-14 | 2 | 2019-10-14 | In Progress
|  | Test case creation | 2019-10-14 | 2 | 2019-10-14 | In Progress
|  | Unit Test | 2019-10-31 | 3 | 2019-10-31 | Not Started
| Backend Developer 5 | Peer code review (backend) | 2019-10-29 | 12 | 2019-10-30 | Not Started
SP2-00022 | Backend Developer 1 | Backend dev | 2019-10-22 | 24 | 2019-10-25 | Not Started
|  | Code Quality Check (backend) | 2019-10-28 | 1 | 2019-10-28 | Not Started
|  | Demo | 2019-10-29 | 1 | 2019-10-30 | Not Started
|  | SIT | 2019-10-29 | 4 | 2019-10-29 | Not Started
|  | Technical discussion (Backend) | 2019-10-21 | 1 | 2019-10-21 | Not Started
|  | Test case creation | 2019-10-21 | 3 | 2019-10-22 | Not Started
|  | Unit Test | 2019-10-28 | 4 | 2019-10-28 | Not Started
| Backend Developer 4 | Peer code review (backend) | 2019-10-17 | 2 | 2019-10-17 | Completed
| Frontend Developer 4 | Peer code review (Frontend) | 2019-10-31 | 6 | 2019-10-31 | Not Started
| Frontend Developer 5 | Code Quality Check (Frontend) | 2019-10-30 | 4 | 2019-10-30 | Not Started
|  | Demo | 2019-10-31 | 1 | 2019-10-31 | Not Started
|  | Frontend dev | 2019-10-28 | 6 | 2019-10-29 | Not Started
|  | SIT | 2019-10-30 | 4 | 2019-10-31 | Not Started
|  | Technical discussion (Frontend) | 2019-10-24 | 3 | 2019-10-25 | Not Started
|  | Test case creation | 2019-10-28 | 2 | 2019-10-28 | Not Started
Grand Total
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Working
Scrum Team Management Dashboard
Today Date: | 2019-10-20
Project Start Date: | 2019-03-01
Project End Date: | 2019-12-31
Current Sprint Start: | 2019-10-01
Current Sprint End: | 2019-10-31
Days Total: | 30
Days Completed: | 19 | 63.33%
Days Remaining: | 11 | 36.67%
Scroll Bar | 0
Column Labels
| Completed | In Progress | Not Started | Grand Total
Count of Story # | 104 | 8 | 44 | 156
Sprint Number | _Accepted Story Point | _Planned Story Point | _Completed Story Point
S01 | 158 | 174.6 | 165
S02 | 160 | 174.6 | 174
S03 | 183 | 183.6 | 183
S04 | 172 | 182.7 | 182
S05 | 150 | 163.8 | 163
S06 | 150 | 157.5 | 157
S07 | 151 | 157.5 | 157
S08 | 130 | 150.3 | 140
S09
S10
Grand Total | 1254 | 1344.6 | 1321

## Story List
Issue key | Summary | Status | Story Points
SP2-00001 | Story 1 | Closed | 5
SP2-00002 | Story 2 | Closed | 5
SP2-00003 | Story 3 | Closed | 8
SP2-00004 | Story 4 | Closed | 3
SP2-00005 | Story 5 | Closed | 8
SP2-00006 | Story 6 | Closed | 5
SP2-00007 | Story 7 | Closed | 5
SP2-00008 | Story 8 | Closed | 5
SP2-00009 | Story 9 | Closed | 8
SP2-00010 | Story 10 | Closed | 5
SP2-00011 | Story 11 | Closed | 5
SP2-00012 | Story 12 | In-Progress | 8
SP2-00013 | Story 13 | In-Progress | 8
SP2-00014 | Story 14 | In-Progress | 5
SP2-00015 | Story 15 | In-Progress | 3
SP2-00016 | Story 16 | In-Progress | 5
SP2-00017 | Story 17 | In-Progress | 8
SP2-00018 | Story 18 | In-Progress | 5
SP2-00019 | Story 19 | In-Progress | 5
SP2-00020 | Story 20 | In-Progress | 5
SP2-00021 | Story 21 | In-Progress | 8
SP2-00022 | Story 22 | In-Progress | 5
SP2-00023 | Story 23 | Open | 8
SP2-00024 | Story 24 | Open | 5
SP2-00025 | Story 25 | Open | 5
SP2-00026 | Story 26 | Open | 5

## Task List
Story # | Story descriptio | Task Name | Assignee | Duration (Hr) | Start Date | End Date | Status
SP2-00001 | Story 1 | Release preparation | Backend Developer 1 | 5 | 2019-10-02 | 2019-10-02 | Completed
SP2-00001 | Story 1 | Release preparation | Backend Developer 2 | 5 | 2019-10-02 | 2019-10-02 | Completed
SP2-00001 | Story 1 | Release preparation | Frontend Developer 1 | 5 | 2019-10-01 | 2019-10-01 | Completed
SP2-00001 | Story 1 | Release preparation | Frontend Developer 2 | 5 | 2019-10-01 | 2019-10-01 | Completed
SP2-00001 | Story 1 | Release deployment | Backend Developer 3 | 4 | 2019-10-02 | 2019-10-02 | Completed
SP2-00002 | Story 2 | Release deployment | Frontend Developer 1 | 6 | 2019-10-02 | 2019-10-02 | Completed
SP2-00002 | Story 2 | Release deployment | Backend Developer 1 | 2 | 2019-10-03 | 2019-10-03 | Completed
SP2-00002 | Story 2 | Code Quality Check (Frontend) | Frontend Developer 2 | 6 | 2019-10-02 | 2019-10-02 | Completed
SP2-00003 | Story 3 | Incident Investigation | Frontend Developer 1 | 8 | 2019-10-03 | 2019-10-04 | Completed
SP2-00003 | Story 3 | Incident Investigation | Backend Developer 3 | 6 | 2019-10-02 | 2019-10-03 | Completed
SP2-00003 | Story 3 | Incident Investigation | Frontend Developer 2 | 8 | 2019-10-03 | 2019-10-04 | Completed
SP2-00004 | Story 4 | Incident Investigation | Backend Developer 4 | 8 | 2019-10-02 | 2019-10-03 | Completed
SP2-00004 | Story 4 | Incident Investigation | Backend Developer 5 | 8 | 2019-10-02 | 2019-10-03 | Completed
SP2-00004 | Story 4 | Incident Investigation | Backend Developer 3 | 6 | 2019-10-03 | 2019-10-04 | Completed
SP2-00004 | Story 4 | Incident Investigation | Frontend Developer 2 | 8 | 2019-10-04 | 2019-10-07 | Completed
SP2-00004 | Story 4 | Incident Investigation | Frontend Developer 2 | 8 | 2019-10-08 | 2019-10-09 | Completed
SP2-00004 | Story 4 | Incident Investigation | Frontend Developer 3 | 8 | 2019-10-01 | 2019-10-02 | Completed
SP2-00005 | Story 5 | Technical discussion (Backend) | Backend Developer 4 | 3 | 2019-10-03 | 2019-10-03 | Completed
SP2-00005 | Story 5 | Test case creation | Backend Developer 3 | 6 | 2019-10-04 | 2019-10-07 | Completed
SP2-00005 | Story 5 | Frontend dev | Backend Developer 5 | 8 | 2019-10-03 | 2019-10-04 | Completed
SP2-00005 | Story 5 | Peer code review (Frontend) | Frontend Developer 1 | 8 | 2019-10-07 | 2019-10-08 | Completed
SP2-00005 | Story 5 | Code Quality Check (Frontend) | Frontend Developer 3 | 8 | 2019-10-02 | 2019-10-03 | Completed
SP2-00005 | Story 5 | SIT | Frontend Developer 2 | 8 | 2019-10-09 | 2019-10-10 | Completed
SP2-00006 | Story 6 | Demo | Frontend Developer 3 | 2 | 2019-10-03 | 2019-10-03 | Completed
SP2-00006 | Story 6 | WA dev | Frontend Developer 3 | 24 | 2019-10-03 | 2019-10-09 | Completed
SP2-00006 | Story 6 | Frontend dev | Frontend Developer 3 | 24 | 2019-10-09 | 2019-10-15 | Completed
SP2-00006 | Story 6 | Peer code review (Frontend) | Frontend Developer 2 | 2 | 2019-10-10 | 2019-10-10 | Completed
SP2-00006 | Story 6 | Code Quality Check (Frontend) | Frontend Developer 3 | 2 | 2019-10-15 | 2019-10-15 | Completed
SP2-00006 | Story 6 | SIT | Frontend Developer 3 | 18 | 2019-10-16 | 2019-10-18 | Completed
SP2-00006 | Story 6 | Demo | Frontend Developer 3 | 2 | 2019-10-21 | 2019-10-21 | Not Started
SP2-00006 | Story 6 | WA dev | Frontend Developer 3 | 24 | 2019-10-22 | 2019-10-31 | Not Started
SP2-00007 | Story 7 | Technical discussion (Frontend) | Frontend Developer 2 | 4 | 2019-10-11 | 2019-10-11 | Completed
SP2-00007 | Story 7 | Test case creation | Frontend Developer 2 | 4 | 2019-10-14 | 2019-10-14 | Completed
SP2-00007 | Story 7 | Frontend dev | Frontend Developer 2 | 30 | 2019-10-15 | 2019-10-21 | In Progress
SP2-00007 | Story 7 | Peer code review (Frontend) | Frontend Developer 5 | 4 | 2019-10-01 | 2019-10-01 | Completed
SP2-00007 | Story 7 | Code Quality Check (Frontend) | Frontend Developer 2 | 4 | 2019-10-22 | 2019-10-22 | Not Started
SP2-00007 | Story 7 | SIT | Frontend Developer 2 | 8 | 2019-10-23 | 2019-10-24 | Not Started
SP2-00007 | Story 7 | Demo | Frontend Developer 2 | 2 | 2019-10-25 | 2019-10-25 | Not Started
SP2-00007 | Story 7 | WA dev | Frontend Developer 2 | 24 | 2019-10-28 | 2019-10-31 | Not Started
SP2-00008 | Story 8 | Technical Discussion (Backend) | Backend Developer 5 | 3 | 2019-10-07 | 2019-10-07 | Completed
SP2-00008 | Story 8 | Test case creation | Backend Developer 5 | 3 | 2019-10-07 | 2019-10-07 | Completed
SP2-00008 | Story 8 | Backend dev | Backend Developer 5 | 6 | 2019-10-08 | 2019-10-08 | Completed
SP2-00008 | Story 8 | Peer code review (backend) | Backend Developer 2 | 2 | 2019-10-02 | 2019-10-03 | Completed
SP2-00008 | Story 8 | Code Quality Check (backend) | Backend Developer 5 | 2 | 2019-10-09 | 2019-10-09 | Completed
SP2-00008 | Story 8 | Unit Test | Backend Developer 5 | 4 | 2019-10-09 | 2019-10-09 | Completed
SP2-00008 | Story 8 | SIT | Backend Developer 5 | 3 | 2019-10-10 | 2019-10-10 | Completed
SP2-00009 | Story 9 | Technical Discussion (Backend) | Backend Developer 5 | 3 | 2019-10-10 | 2019-10-10 | Completed
SP2-00009 | Story 9 | Test case creation | Backend Developer 5 | 2 | 2019-10-11 | 2019-10-11 | Completed
SP2-00009 | Story 9 | Backend dev | Backend Developer 5 | 8 | 2019-10-11 | 2019-10-14 | Completed
SP2-00009 | Story 9 | Peer code review (backend) | Backend Developer 1 | 2 | 2019-10-03 | 2019-10-03 | Completed
SP2-00009 | Story 9 | Code Quality Check (backend) | Backend Developer 5 | 1 | 2019-10-14 | 2019-10-14 | Completed
SP2-00009 | Story 9 | Unit Test | Backend Developer 5 | 3 | 2019-10-15 | 2019-10-15 | Completed
SP2-00009 | Story 9 | SIT | Backend Developer 5 | 3 | 2019-10-15 | 2019-10-15 | Completed
SP2-00010 | Story 10 | Technical Discussion (Frontend) | Frontend Developer 5 | 4 | 2019-10-01 | 2019-10-02 | Completed
SP2-00010 | Story 10 | Technical Discussion (Backend) | Backend Developer 3 | 2 | 2019-10-07 | 2019-10-07 | Completed
SP2-00010 | Story 10 | Test case creation | Backend Developer 3 | 2 | 2019-10-07 | 2019-10-07 | Completed
SP2-00010 | Story 10 | CMS dev | Frontend Developer 5 | 8 | 2019-10-02 | 2019-10-03 | Completed
SP2-00010 | Story 10 | Frontend dev | Frontend Developer 5 | 6 | 2019-10-04 | 2019-10-04 | Completed
SP2-00010 | Story 10 | Peer code review (Frontend) | Frontend Developer 5 | 2 | 2019-10-07 | 2019-10-07 | Completed
SP2-00010 | Story 10 | WA dev | Frontend Developer 5 | 3 | 2019-10-07 | 2019-10-08 | Completed
SP2-00010 | Story 10 | Code Quality Check (Frontend) | Frontend Developer 5 | 2 | 2019-10-08 | 2019-10-08 | Completed
SP2-00010 | Story 10 | Backend dev | Backend Developer 3 | 6 | 2019-10-08 | 2019-10-08 | Completed
SP2-00010 | Story 10 | Peer code review (backend) | Backend Developer 2 | 2 | 2019-10-03 | 2019-10-03 | Completed
SP2-00010 | Story 10 | Code Quality Check (backend) | Backend Developer 3 | 1 | 2019-10-09 | 2019-10-09 | Completed
SP2-00010 | Story 10 | Unit Test | Backend Developer 3 | 4 | 2019-10-09 | 2019-10-09 | Completed
SP2-00010 | Story 10 | SIT | Backend Developer 3 | 7 | 2019-10-10 | 2019-10-11 | Completed
SP2-00010 | Story 10 | demo | Backend Developer 3 | 1 | 2019-10-11 | 2019-10-11 | Completed
SP2-00011 | Story 11 | Technical discussion (Frontend) | Frontend Developer 1 | 8 | 2019-10-08 | 2019-10-09 | Completed
SP2-00011 | Story 11 | Technical discussion (Frontend) | Frontend Developer 4 | 8 | 2019-10-01 | 2019-10-02 | Completed
SP2-00011 | Story 11 | Backend dev | Backend Developer 1 | 24 | 2019-10-04 | 2019-10-09 | Completed
SP2-00011 | Story 11 | Technical discussion (Backend) | Backend Developer 5 | 8 | 2019-10-16 | 2019-10-17 | Completed
SP2-00011 | Story 11 | Technical discussion (Backend) | Frontend Developer 4 | 8 | 2019-10-02 | 2019-10-03 | Completed
SP2-00012 | Story 12 | Technical discussion (Backend) | Backend Developer 2 | 6 | 2019-10-04 | 2019-10-04 | Completed
SP2-00012 | Story 12 | Backend dev | Backend Developer 2 | 24 | 2019-10-07 | 2019-10-10 | Completed
SP2-00012 | Story 12 | SIT | Backend Developer 2 | 6 | 2019-10-11 | 2019-10-11 | Completed
SP2-00012 | Story 12 | Technical discussion (Backend) | Backend Developer 2 | 2 | 2019-10-14 | 2019-10-14 | Completed
SP2-00013 | Story 13 | SIT | Backend Developer 2 | 2 | 2019-10-14 | 2019-10-14 | Completed
SP2-00014 | Story 14 | Technical Discussion (Frontend) | Frontend Developer 4 | 4 | 2019-10-04 | 2019-10-04 | Completed
SP2-00014 | Story 14 | Test case creation | Frontend Developer 4 | 2 | 2019-10-04 | 2019-10-04 | Completed
SP2-00014 | Story 14 | CMS dev | Frontend Developer 4 | 2 | 2019-10-07 | 2019-10-07 | Completed
SP2-00014 | Story 14 | Frontend dev | Frontend Developer 4 | 30 | 2019-10-08 | 2019-10-14 | Completed
SP2-00014 | Story 14 | Peer code review (Frontend) | Frontend Developer 5 | 2 | 2019-10-08 | 2019-10-08 | Completed
SP2-00014 | Story 14 | Code Quality Check (Frontend) | Frontend Developer 4 | 1 | 2019-10-15 | 2019-10-15 | Completed
SP2-00014 | Story 14 | SIT | Frontend Developer 4 | 1 | 2019-10-15 | 2019-10-15 | Completed
SP2-00014 | Story 14 | demo | Frontend Developer 4 | 1 | 2019-10-15 | 2019-10-15 | Completed
SP2-00015 | Story 15 | Technical discussion (Frontend) | Backend Developer 3 | 8 | 2019-10-11 | 2019-10-14 | Completed
SP2-00015 | Story 15 | Technical discussion (Frontend) | Frontend Developer 5 | 8 | 2019-10-09 | 2019-10-10 | Completed
SP2-00016 | Story 16 | Technical discussion (Backend) | Backend Developer 2 | 4 | 2019-10-18 | 2019-10-21 | Completed
SP2-00016 | Story 16 | Test case creation | Backend Developer 1 | 1 | 2019-10-10 | 2019-10-10 | Completed
SP2-00016 | Story 16 | Backend dev | Backend Developer 1 | 9 | 2019-10-10 | 2019-10-11 | Completed
SP2-00016 | Story 16 | Peer code review (backend) | Backend Developer 4 | 2 | 2019-10-04 | 2019-10-04 | Completed
SP2-00016 | Story 16 | Code Quality Check (backend) | Backend Developer 1 | 2 | 2019-10-21 | 2019-10-21 | Not Started
SP2-00016 | Story 16 | Unit Test | Backend Developer 2 | 6 | 2019-10-21 | 2019-10-21 | Not Started
SP2-00016 | Story 16 | SIT | Backend Developer 2 | 6 | 2019-10-22 | 2019-10-22 | Not Started
SP2-00016 | Story 16 | demo | Backend Developer 2 | 6 | 2019-10-23 | 2019-10-23 | Not Started
SP2-00017 | Story 17 | Technical Discussion (Backend) | Backend Developer 4 | 2 | 2019-10-04 | 2019-10-04 | Completed
SP2-00017 | Story 17 | Test case creation | Backend Developer 4 | 2 | 2019-10-07 | 2019-10-07 | Completed
SP2-00017 | Story 17 | Backend dev | Backend Developer 4 | 24 | 2019-10-07 | 2019-10-11 | Completed
SP2-00017 | Story 17 | Peer code review (backend) | Backend Developer 1 | 1 | 2019-10-21 | 2019-10-21 | Not Started
SP2-00017 | Story 17 | Code Quality Check (backend) | Backend Developer 4 | 1 | 2019-10-14 | 2019-10-14 | Completed
SP2-00017 | Story 17 | Unit Test | Backend Developer 4 | 4 | 2019-10-14 | 2019-10-14 | Completed
SP2-00017 | Story 17 | SIT | Backend Developer 4 | 18 | 2019-10-14 | 2019-10-17 | Completed
SP2-00017 | Story 17 | Demo | Backend Developer 4 | 1 | 2019-10-17 | 2019-10-17 | Completed
SP2-00018 | Story 18 | Technical Discussion (Frontend) | Frontend Developer 4 | 2 | 2019-10-15 | 2019-10-15 | Completed
SP2-00018 | Story 18 | Test case creation | Frontend Developer 4 | 1 | 2019-10-15 | 2019-10-15 | Completed
SP2-00018 | Story 18 | CMS dev | Frontend Developer 4 | 24 | 2019-10-16 | 2019-10-21 | In Progress
SP2-00018 | Story 18 | Frontend dev | Frontend Developer 4 | 4 | 2019-10-22 | 2019-10-22 | Not Started
SP2-00018 | Story 18 | Peer code review (Frontend) | Frontend Developer 5 | 2 | 2019-10-10 | 2019-10-10 | Completed
SP2-00018 | Story 18 | Code Quality Check (Frontend) | Frontend Developer 4 | 1 | 2019-10-23 | 2019-10-23 | Not Started
SP2-00018 | Story 18 | SIT | Frontend Developer 4 | 1 | 2019-10-23 | 2019-10-23 | Not Started
SP2-00018 | Story 18 | Demo | Frontend Developer 4 | 1 | 2019-10-23 | 2019-10-23 | Not Started
SP2-00019 | Story 19 | Technical Discussion (Frontend) | Frontend Developer 5 | 2 | 2019-10-10 | 2019-10-10 | Completed
SP2-00019 | Story 19 | Test case creation | Frontend Developer 5 | 2 | 2019-10-11 | 2019-10-11 | Completed
SP2-00019 | Story 19 | CMS dev | Frontend Developer 5 | 22 | 2019-10-11 | 2019-10-17 | Completed
SP2-00019 | Story 19 | Frontend dev | Frontend Developer 5 | 24 | 2019-10-17 | 2019-10-22 | In Progress
SP2-00019 | Story 19 | Peer code review (Frontend) | Frontend Developer 4 | 2 | 2019-10-23 | 2019-10-23 | Not Started
SP2-00019 | Story 19 | Code Quality Check (Frontend) | Frontend Developer 5 | 2 | 2019-10-23 | 2019-10-23 | Not Started
SP2-00019 | Story 19 | SIT | Frontend Developer 5 | 2 | 2019-10-23 | 2019-10-23 | Not Started
SP2-00019 | Story 19 | Demo | Frontend Developer 5 | 1 | 2019-10-23 | 2019-10-23 | Not Started
SP2-00019 | Story 19 | WA dev | Frontend Developer 5 | 4 | 2019-10-24 | 2019-10-24 | Not Started
SP2-00020 | Story 20 | Technical Discussion (Frontend) | Frontend Developer 1 | 2 | 2019-10-09 | 2019-10-09 | Completed
SP2-00020 | Story 20 | Test case creation | Frontend Developer 1 | 6 | 2019-10-10 | 2019-10-10 | Completed
SP2-00020 | Story 20 | CMS dev | Frontend Developer 1 | 24 | 2019-10-11 | 2019-10-16 | Completed
SP2-00020 | Story 20 | Frontend dev | Frontend Developer 1 | 24 | 2019-10-17 | 2019-10-22 | In Progress
SP2-00020 | Story 20 | Peer code review (Frontend) | Frontend Developer 5 | 2 | 2019-10-24 | 2019-10-24 | Not Started
SP2-00020 | Story 20 | Code Quality Check (Frontend) | Frontend Developer 1 | 6 | 2019-10-30 | 2019-10-30 | Not Started
SP2-00020 | Story 20 | Demo | Frontend Developer 1 | 1 | 2019-10-31 | 2019-10-31 | Not Started
SP2-00020 | Story 20 | Technical Discussion (Backend) | Backend Developer 5 | 1 | 2019-10-17 | 2019-10-17 | Completed
SP2-00020 | Story 20 | Backend dev | Backend Developer 5 | 4 | 2019-10-18 | 2019-10-18 | Completed
SP2-00020 | Story 20 | Peer code review (backend) | Backend Developer 3 | 1 | 2019-10-14 | 2019-10-14 | In Progress
SP2-00020 | Story 20 | Code Quality Check (backend) | Backend Developer 5 | 1 | 2019-10-18 | 2019-10-18 | Completed
SP2-00020 | Story 20 | Unit Test | Backend Developer 5 | 2 | 2019-10-28 | 2019-10-28 | Not Started
SP2-00020 | Story 20 | SIT | Backend Developer 5 | 4 | 2019-10-28 | 2019-10-28 | Not Started
SP2-00021 | Story 21 | Technical Discussion (Backend) | Backend Developer 3 | 2 | 2019-10-14 | 2019-10-14 | In Progress
SP2-00021 | Story 21 | Test case creation | Backend Developer 3 | 2 | 2019-10-14 | 2019-10-14 | In Progress
SP2-00021 | Story 21 | Backend dev | Backend Developer 3 | 24 | 2019-10-15 | 2019-10-18 | In Progress
SP2-00021 | Story 21 | Peer code review (backend) | Backend Developer 5 | 12 | 2019-10-29 | 2019-10-30 | Not Started
SP2-00021 | Story 21 | Code Quality Check (backend) | Backend Developer 3 | 1 | 2019-10-31 | 2019-10-31 | Not Started
SP2-00021 | Story 21 | Unit Test | Backend Developer 3 | 3 | 2019-10-31 | 2019-10-31 | Not Started
SP2-00021 | Story 21 | SIT | Backend Developer 3 | 2 | 2019-10-31 | 2019-10-31 | Not Started
SP2-00021 | Story 21 | Demo | Backend Developer 3 | 1 | 2019-10-31 | 2019-10-31 | Not Started
SP2-00022 | Story 22 | Technical Discussion (Frontend) | Frontend Developer 5 | 3 | 2019-10-24 | 2019-10-25 | Not Started
SP2-00022 | Story 22 | Test case creation | Frontend Developer 5 | 2 | 2019-10-28 | 2019-10-28 | Not Started
SP2-00022 | Story 22 | Frontend dev | Frontend Developer 5 | 6 | 2019-10-28 | 2019-10-29 | Not Started
SP2-00022 | Story 22 | Peer code review (Frontend) | Frontend Developer 4 | 6 | 2019-10-31 | 2019-10-31 | Not Started
SP2-00022 | Story 22 | Code Quality Check (Frontend) | Frontend Developer 5 | 4 | 2019-10-30 | 2019-10-30 | Not Started
SP2-00022 | Story 22 | SIT | Frontend Developer 5 | 4 | 2019-10-30 | 2019-10-31 | Not Started
SP2-00022 | Story 22 | Demo | Frontend Developer 5 | 1 | 2019-10-31 | 2019-10-31 | Not Started
SP2-00022 | Story 22 | Technical Discussion (Backend) | Backend Developer 1 | 1 | 2019-10-21 | 2019-10-21 | Not Started
SP2-00022 | Story 22 | Test case creation | Backend Developer 1 | 3 | 2019-10-21 | 2019-10-22 | Not Started
SP2-00022 | Story 22 | Backend dev | Backend Developer 1 | 24 | 2019-10-22 | 2019-10-25 | Not Started
SP2-00022 | Story 22 | Peer code review (backend) | Backend Developer 4 | 2 | 2019-10-17 | 2019-10-17 | Completed
SP2-00022 | Story 22 | Code Quality Check (backend) | Backend Developer 1 | 1 | 2019-10-28 | 2019-10-28 | Not Started
SP2-00022 | Story 22 | Unit Test | Backend Developer 1 | 4 | 2019-10-28 | 2019-10-28 | Not Started
SP2-00022 | Story 22 | SIT | Backend Developer 1 | 4 | 2019-10-29 | 2019-10-29 | Not Started
SP2-00022 | Story 22 | Demo | Backend Developer 1 | 1 | 2019-10-29 | 2019-10-30 | Not Started

## Team member
|  | Sprint 1 |  |  | Sprint 2 |  |  | Sprint 3 |  |  | Sprint 4 |  |  | Sprint 5 |  |  | Sprint 6 |  |  |  | Sprint 7 |  | Sprint 8
Member Name | Velocity per day | # of annual leave | # of workdays | Actual Velocity | # of annual leave2 | # of workdays2 | Actual Velocity2 | # of annual leave3 | # of workdays3 | Actual Velocity3 | # of annual leave4 | # of workdays4 | Actual Velocity4 | # of annual leave5 | # of workdays5 | Actual Velocity5 | # of annual leave6 | # of workdays6 | Actual Velocity6 | # of annual leave7 | # of workdays7 | Actual Velocity7 | # of annual leave8 | # of workdays8 | Actual Velocity8
Backend Developer 1 | 0.9 | 0 | 21 | 18.9 | 5 | 16 | 14.4 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 5 | 16 | 14.4
Backend Developer 2 | 0.9 | 2 | 19 | 17.1 | 2 | 19 | 17.1 | 2 | 19 | 17.1 | 2 | 19 | 17.1 | 1 | 20 | 18 | 5 | 16 | 14.4 | 5 | 16 | 14.4 | 3 | 18 | 16.2
Backend Developer 3 | 0.9 | 4 | 17 | 15.3 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 6 | 15 | 13.5
Backend Developer 4 | 0.9 | 0 | 21 | 18.9 | 3 | 18 | 16.2 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 1 | 20 | 18 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 10 | 11 | 9.9
Backend Developer 5 | 0.9 | 6 | 15 | 13.5 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 1 | 20 | 18 | 1 | 20 | 18 | 5 | 16 | 14.4 | 5 | 16 | 14.4 | 5 | 16 | 14.4
Frontend Developer 1 | 0.9 | 0 | 21 | 18.9 | 2 | 19 | 17.1 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 5 | 16 | 14.4
Frontend Developer 2 | 0.9 | 2 | 19 | 17.1 | 2 | 19 | 17.1 | 2 | 19 | 17.1 | 2 | 19 | 17.1 | 2 | 19 | 17.1 | 2 | 19 | 17.1 | 2 | 19 | 17.1 | 0 | 21 | 18.9
Frontend Developer 3 | 0.9 | 2 | 19 | 17.1 | 1 | 20 | 18 | 2 | 19 | 17.1 | 2 | 19 | 17.1 | 2 | 19 | 17.1 | 2 | 19 | 17.1 | 2 | 19 | 17.1 | 4 | 17 | 15.3
Frontend Developer 4 | 0.9 | 0 | 21 | 18.9 | 1 | 20 | 18 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 5 | 16 | 14.4
Frontend Developer 5 | 0.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 0 | 21 | 18.9 | 21 | 0 | 0 | 21 | 0 | 0 | 21 | 0 | 0 | 0 | 21 | 18.9
Total |  |  | 194 | 174.6 |  | 194 | 174.6 |  | 204 | 183.6 |  | 203 | 182.7 |  | 182 | 163.8 |  | 175 | 157.5 |  | 175 | 157.5 |  | 167 | 150.3

## Sprint Summary
Sprint Number | Sprint Start Date | Sprint End Date | # of days in Sprint | # of Planned Story | Planned Story Point | # of Completed Story | Completed Story Point | # of Accepted Story | Accepted Story Point
S01 | 2019-03-01 | 2019-03-31 | 21 | 30 | 174.6 | 28 | 165 | 26 | 158
S02 | 2019-04-01 | 2019-04-30 | 19 | 28 | 174.6 | 28 | 174 | 25 | 160
S03 | 2019-05-01 | 2019-05-31 | 21 | 28 | 183.6 | 28 | 183 | 28 | 183
S04 | 2019-06-01 | 2019-06-30 | 19 | 30 | 182.7 | 28 | 182 | 26 | 172
S05 | 2019-07-01 | 2019-07-31 | 22 | 28 | 163.8 | 28 | 163 | 26 | 150
S06 | 2019-08-01 | 2019-08-31 | 22 | 28 | 157.5 | 28 | 157 | 26 | 150
S07 | 2019-09-01 | 2019-09-30 | 21 | 27 | 157.5 | 27 | 157 | 26 | 151
S08 | 2019-10-01 | 2019-10-31 | 21 | 26 | 150.3 | 24 | 140 | 22 | 130
S09 | 2019-11-01 | 2019-11-30 | 21
S10 | 2019-12-01 | 2019-12-31 | 20

## Public Holiday
Holiday Date
2019-01-01
2019-02-05
2019-02-06
2019-04-05
2019-04-19
2019-04-20
2019-04-22
2019-05-01
2019-05-12
2019-05-13
2019-06-07
2019-07-01
2019-09-14
2019-10-01
2019-10-07
2019-12-25
2019-12-26

## Task item
Task
Technical discussion (Frontend)
Technical discussion (Backend)
Release preparation
Release deployment
Incident Investigation
Test case creation
CMS dev
WA dev
Frontend dev
Peer code review (Frontend)
Code Quality Check (Frontend)
Backend dev
Peer code review (backend)
Code Quality Check (backend)
Unit Test
SIT
Demo